## Stakeholder Register
Stakeholder | Department | Role | Influence | Interest | Primary Responsibilities | PMS Areas | Engagement / Communication
General Manager | Management | Project Sponsor | High | High | Business approval, priorities, go-live approval | All modules | Steering meetings; milestone reviews
Front Office Manager | Front Office | Process Owner | High | High | Reservations, room allocation, check-in/out, front-office workflows | Reservations; Front Office; Folio | Process workshops; UAT; weekly reviews
Reservation Manager | Reservations | Process Owner | Medium | High | Reservation creation, modification, cancellation and confirmation | Reservations; Availability | Requirement workshops; UAT
Housekeeping Manager | Housekeeping | Process Owner | High | High | Room status, cleaning, inspection and room readiness | Housekeeping; Room Status | Process workshops; UAT; training
F&B Manager | Food & Beverage | Process Owner | Medium | High | Restaurant operations and POS transaction workflows | POS; PMS Integration | Integration workshops; UAT
Finance Manager | Finance | Process Owner | High | High | Billing, payments, folios, reconciliation and finance controls | Folio; Billing; Payments | Requirement workshops; UAT; sign-off
IT Manager | IT | Technical Owner | High | High | User access, technical coordination, integrations and issue escalation | Integrations; Security; Data | Technical workshops; defect reviews
PMS Implementation Analyst | Implementation | Implementation Lead | High | High | Discovery, requirements, process mapping, configuration support, UAT, training and go-live | All modules | Daily coordination; status reporting
Front Office Users | Front Office | End Users | Medium | High | Execute reservations, check-in/out and guest folio activities | Reservations; Front Office; Folio | Training; UAT; hypercare
Housekeeping Users | Housekeeping | End Users | Medium | High | Update room status and housekeeping activities | Housekeeping; Room Status | Training; UAT; hypercare
F&B Users | Food & Beverage | End Users | Medium | Medium | Process restaurant transactions and room postings | POS; PMS Integration | Training; integration UAT
Finance Users | Finance | End Users | Medium | High | Billing, payment posting and reconciliation | Folio; Billing; Payments | Training; UAT