## RTM
Business Requirement ID | Business Requirement | Functional Requirement ID | PMS Module | Configuration / Implementation Area | UAT Test Case ID | Status
BR-001 | Centralized reservation management | FR-001 | Reservations | Reservation creation, guest details, stay dates, room type and rate plan | UAT-001 | Planned
BR-002 | Real-time room availability | FR-002 | Reservations / Front Office | Room inventory and availability rules | UAT-002 | Planned
BR-003 | Room allocation | FR-003 | Front Office | Room assignment by room type and availability | UAT-003 | Planned
BR-004 | Guest check-in | FR-006 | Front Office | Check-in workflow, guest verification and room assignment | UAT-004 | Planned
BR-005 | Guest checkout | FR-010 | Front Office | Checkout workflow, folio settlement and room status update | UAT-005 | Planned
BR-006 | Guest folio and billing | FR-015 | Front Office / Finance | Room charges, service charges, taxes, payments and balance | UAT-006 | Planned
BR-007 | Housekeeping room status | FR-012 | Housekeeping | Dirty, cleaning, clean, inspected/ready status workflow | UAT-007 | Planned
BR-008 | POS charge posting | FR-018 | F&B / PMS | Restaurant charge posting to guest folio | UAT-008 | Planned
BR-009 | Guest profile management | FR-011 | Reservations / Front Office | Guest profile creation, update and duplicate prevention | UAT-009 | Planned
BR-010 | Data migration | FR-020 | Data Migration | Guest and reservation data mapping, cleansing and validation | UAT-010 | Planned
BR-011 | Role-based access | FR-022 | Administration / Security | Department-based access and permissions | UAT-011 | Planned
BR-012 | Operational reporting | FR-023 | Reporting | Occupancy, arrivals, departures, room status and revenue reports | UAT-012 | Planned
BR-013 | Audit and traceability | FR-024 | Administration / Audit | Track key user and transaction changes | UAT-013 | Planned
BR-014 | Error handling | FR-025 | All Modules | Validation messages and controlled error handling | UAT-014 | Planned
BR-015 | Integration validation | FR-019 | Integration | Validate interface response, posting and reconciliation | UAT-015 | Planned

## Traceability_Legend
Field | Purpose
Business Requirement ID | Links the item back to the BRD.
Functional Requirement ID | Links the business need to system behavior defined in the FRD.
PMS Module | Identifies the functional area impacted.
Configuration / Implementation Area | Shows what would need to be configured or prepared during implementation.
UAT Test Case ID | Links the requirement to the corresponding acceptance test.
Status | Current portfolio planning status; updated during implementation/UAT.