## GAP Analysis
Gap ID | Area | Process / Capability | AS-IS | TO-BE | Identified Gap / Risk | Priority | Solution / Implementation Approach | Owner | Validation
GAP-001 | Reservations | Reservation management | Excel + phone/email | Centralized PMS reservation workflow | No single reservation record; duplicate/outdated availability risk | High | Configure PMS reservation workflow and booking sources | Reservations Manager | UAT-001
GAP-002 | Reservations | Room availability | Manual Excel checking | Real-time room inventory | Availability can become outdated between updates | High | Configure room inventory, room types and availability rules | PMS Implementation Analyst | UAT-002
GAP-003 | Front Office | Room allocation | Manual assignment | PMS-assisted room assignment | Risk of assigning unavailable rooms | High | Configure room assignment and room-status dependencies | Front Office Manager | UAT-003
GAP-004 | Front Office | Guest check-in | Manual lookup | Structured PMS check-in workflow | Longer check-in and inconsistent data capture | High | Configure check-in workflow and mandatory guest fields | Front Office Manager | UAT-004
GAP-005 | Housekeeping | Room status | Phone/register/manual updates | Centralized room-status workflow | Front desk may not have current room readiness | High | Configure room status lifecycle and housekeeping updates | Housekeeping Manager | UAT-007
GAP-006 | F&B / PMS | Charge posting | Standalone POS + manual posting | POS-to-PMS folio posting | Manual posting creates delay/reconciliation risk | High | Define and test POS-PMS interface; validate guest/room mapping | IT Manager | UAT-008
GAP-007 | Finance | Guest folio | Manual billing/reconciliation | Centralized guest folio | Charges require manual consolidation | High | Configure charge codes, taxes, payments and folio rules | Finance Manager | UAT-006
GAP-008 | Guest Data | Guest profiles | Separate spreadsheets | Centralized guest profile | Duplicate/inconsistent guest records | Medium | Define guest master fields, duplicate checks and migration rules | Reservations Manager | UAT-009
GAP-009 | Data Migration | Legacy data | Excel files | Validated PMS data | Duplicates, blanks and inconsistent formats | High | Mapping, cleansing, test migration and reconciliation | Implementation Analyst | UAT-010
GAP-010 | Administration | User access | Manual/shared access | Role-based PMS access | Risk of inappropriate access | High | Configure department roles and permissions | IT Manager | UAT-011
GAP-011 | Reporting | Operational reporting | Manual consolidation | Centralized PMS reporting | Reports take time to prepare | Medium | Define report requirements and validate PMS reports | GM / Management | UAT-012
GAP-012 | Audit | Traceability | Limited manual tracking | System audit trail | Difficult to identify changes | Medium | Validate audit logs and user activity tracking | IT Manager | UAT-013
GAP-013 | Integrations | External systems | Disconnected/manual exchange | Defined PMS interfaces | Manual re-entry between systems | High | Document interfaces, mappings, errors and reconciliation | IT Manager | UAT-015
GAP-014 | Operations | Process standardization | Department workarounds | Standardized PMS workflows | Users may follow different processes | Medium | Create TO-BE SOPs and role-based training | Implementation Analyst | UAT-014
GAP-015 | Go-Live | Cutover readiness | No formal checklist | Controlled go-live + hypercare | Operational disruption risk | High | Cutover plan, final validation, sign-off and hypercare | Implementation Lead | UAT-010

## Gap_Method
Field | Purpose
AS-IS | Documents the hotel's current manual/disconnected process.
TO-BE | Defines the intended PMS-enabled future state.
Identified Gap / Risk | Explains the difference or operational risk.
Priority | Implementation attention level for planning.
Solution / Implementation Approach | Configuration, process, integration, migration or training response.
Validation | Links the gap to a future UAT scenario.